## Sheet1
Master Plan
Plan 1 | POC | Epic | Task | Output | Priority | Hours
Setup the project
Requirement Enginneering
|  |  | + Setup github, documents + Setup development environment | The github, documents convention, and developement evironment | 1 | + 1 + 1
Use case definition
|  |  | + Analysis the example of contract + Analysis the Task descriptions + Expectation output template | The type of dataset, type of entity, term, conditions, etc, and the template | 1 | +2 +1 +1
Project organization
|  |  | + Set up a code versioning repository + Setup project documents + Create README | Role of codeing versionning repository Documents management | 1 | +1 +1 +1
10
Model developments
ML solutions
|  |  | + Research the best tools for the project (e.g., OpenAI, Langchain, etc) + Evaluate the right models for the project | The proposal of ML/AI model | 1 | +5 +2
Data Preparation
|  |  | + Load test data via user interface with jupyter nodebook + Read and clean dataset | visualize and present the data | 1 | +1
Model Trainining
|  |  | + Train the model + Tuning the model (if it needs) + Save the model | The ML/AI model with the hyperplance parameters | 1 | +8 +2 +2
Model Experimentation
|  |  | + Evaluate the performance of model | Experimental report with the metrics measurement: + Accuracy + Fluency + Relevance (ROUGE score) + Bias + Coherence etc | 1 | +3
Model Testing
|  |  | + Test model with testing data + Show the result with figure of metric measurement | +A json file with extracted and structed contract conditions +A user interface that allows for the uploading of documents, analysis of tasks, and display of verification results '+ Show (hight light) the unclear from the description of the completed worked whether it may contradict the contract terms +Documents on systems | 1 | + 4 +2
|  |  | + Build the API to serve model and any extra logic that is need to serve it + Test API with POSTMAN API + Package Model serving API in a Docker container + Deploy model serving API on the cloud | JSON file | 1 | +3 +3 +3 +2
40
Total for POC | [5 empty] | 50
Plan 2 | MVP | Epic | Task | Output | Priority | Hours
Model pipeline
Serving & Training optimization
|  |  | + Build the pipeline to automatically run different sequential components such as training, and deploying model |  | 2 | 20
|  |  | + Optimize the model and automate repetitive tasks such as data preprocessing, model training, and evaluation to reduce manual effort and minimize errors. |  | 2 | 15
Monitoring
Monitoring & Dashboaring & CI/CD
|  |  | + Build a dashboard that runs either locally on in the cloud to show the results |  | 2 | 10
Total for MVP | [5 empty] | 95